REFUGIO ANIMAL PARAGUAY

Project Analysis Report

Coverage, Completion & Gap Analysis

Documentation | Epics | Stories | Tasks | Code | Tests

March 26, 2026

Prepared by: Claude Opus 4.6 | AI Whisperers

# Table of Contents

# 1. Executive Summary

Refugio Animal Paraguay is an animal shelter management platform serving the Paraguayan context with European funding network integration. The platform handles adoptions, donations (including international EU donors), animal records, volunteer coordination, and shelter operations.

This report provides a comprehensive analysis of the project's current state: what was planned, what has been built, and what gaps remain.

## 1.1 Project Snapshot

| Source Files | 30 Python files (1,242 lines production code) |
| --- | --- |
| Test Files | 18 test files (2,567 lines, 204 tests passing) |
| Tickets Completed | 10 (RAP-001 through RAP-010), all STATUS: COMPLETED |
| Database Migrations | 4 Alembic migrations applied |
| API Endpoints | 7 routers: animals, adopters, adoption_requests, auth, donations, donors, health |
| Test/Code Ratio | 2.1x (2,567 test lines / 1,242 production lines) |
| Linting | Zero errors (ruff + pyright) |
| Containerization | Multi-stage Dockerfile + docker-compose (PostgreSQL 16 + FastAPI) |

# 2. Planning Inventory

The project has a comprehensive planning structure with 12 epics decomposed into stories and tasks.

## 2.1 Epic Overview

| Epic | Title | Stories | Tasks | Phase | Status |
| --- | --- | --- | --- | --- | --- |
| 0 | Testing Foundation | 4 | 7 | Phase 0 | PARTIAL |
| 1 | Animal Catalog & Management | 5 | 13 | Phase 1 | COMPLETE (API) |
| 2 | Adoption Process & Workflows | 5 | 9 | Phase 1-2 | PARTIAL |
| 3 | Donation & Payment Systems | 4 | 11 | Phase 3 | PARTIAL |
| 4 | Medical Records & Health Mgmt | 4 | 9 | Phase 2-4 | NOT STARTED |
| 5 | Volunteer & Staff Management | 4 | 9 | Phase 2-4 | NOT STARTED |
| 6 | Communications & Notifications | 6 | 13 | Phase 1-2 | NOT STARTED |
| 7 | Admin & Mgmt Dashboards | 4 | 9 | Phase 1-4 | NOT STARTED |
| 8 | Quality Assurance & Testing | 7 | 16 | All | PARTIAL |
| 9 | Deployment & Infrastructure | 4 | 12 | Phase 0+ | PARTIAL |
| 10 | Authentication & User Accounts | 4 | 9 | Phase 1-2 | PARTIAL |
| 11 | Public Portal | 4 | 9 | Phase 1+ | NOT STARTED |

Total: 12 epics, 55 stories, 119 tasks planned.

# 3. Delivery Status by Ticket

10 tickets were completed across Phases 0-2, delivering the full backend API foundation.

## 3.1 Completed Tickets

| Ticket | Deliverable | Key Outputs | Tests |
| --- | --- | --- | --- |
| RAP-001 | Core PostgreSQL schema (animals, adopters, adoption_requests) | 3 tables, GIST constraint, seed data | Validated via migration |
| RAP-002 | SQLAlchemy 2.x ORM models | 3 models, enums, relationships | 30 unit tests |
| RAP-003 | FastAPI scaffold + health endpoint | App, config, session factory, /health | 15 tests |
| RAP-004 | Animals CRUD API | GET/POST/PATCH/DELETE /animals | 34 tests |
| RAP-005 | Adopters CRUD with soft-delete + GDPR | Full CRUD, 409 on dup email | 32 tests |
| RAP-006 | Adoption requests workflow | Status transitions, side effects | 32 tests |
| RAP-007 | JWT authentication (staff/admin) | Login, /me, user creation, RBAC | 24 tests |
| RAP-008 | Animal photo gallery | Photo upload, ordering, cascade | 15 tests |
| RAP-009 | Donations API + Stripe | Donors, donations, PaymentIntent | 26 tests |
| RAP-010 | Docker containerization | Multi-stage build, auto-migrations | Validation only |

# 4. Roadmap vs. Reality

## 4.1 Phase Completion

| Phase | Scope | Timeline | Status |
| --- | --- | --- | --- |
| Phase 0 | Configuration, design, dev environment | Weeks 1-3 | COMPLETE |
| Phase 1 | MVP: Catalog + Adoptions API | Weeks 4-10 | COMPLETE (backend) |
| Phase 2 | Portal + WhatsApp Notifications | Weeks 11-16 | NOT STARTED |
| Phase 3 | Donations + Lost & Found | Weeks 17-23 | PARTIAL (API only) |
| Phase 4 | Community + Content | Weeks 24-30 | NOT STARTED |
| Phase 5 | Stabilization & Scale | Week 31+ | NOT STARTED |

## 4.2 What Is Production-Ready Today

- Full animals catalog API (public read, staff write)

- Full adopters API with soft-delete and GDPR consent tracking

- Complete adoption request workflow with state machine transitions

- Donations API with Stripe PaymentIntent creation

- JWT authentication with staff/admin role separation

- Animal photo gallery with ordering and cascade delete

- Docker containerization with auto-migrations on startup

- Health monitoring endpoint

# 5. Gap Analysis

This section maps what exists against what is planned, identifying critical gaps for launch.

## 5.1 Critical Gaps

| # | Gap | Blocks | Effort | Priority |
| --- | --- | --- | --- | --- |
| 1 | Frontend UI (React/Next.js) | All user-facing features | 4-6 weeks | CRITICAL |
| 2 | Admin dashboard | Staff operations | 2-3 weeks | CRITICAL |
| 3 | Email/WhatsApp notifications | Adoption confirmations | 1-2 weeks | CRITICAL |
| 4 | Stripe webhook processor | Payment completion | 1 week | CRITICAL |
| 5 | CI/CD pipeline (GitHub Actions) | Safe deployments | 1 week | HIGH |
| 6 | Monitoring + logging | Production visibility | 1 week | HIGH |
| 7 | Local payment methods (Tigo Money) | Paraguayan donors | 2 weeks | MEDIUM |
| 8 | Medical records module | Vet workflows | 2-3 weeks | MEDIUM |
| 9 | Volunteer management | Shift scheduling | 2-3 weeks | MEDIUM |
| 10 | Lost & Found system | Community feature | 2 weeks | LOW (Phase 3) |

## 5.2 Planning Quality Issues

Several issues in the planning/ directory need cleanup before further development:

- EPIC-0: 4 stories defined but 0 tasks decomposed — testing foundation is planned but not actionable

- EPIC-2: Duplicate empty story (S02-adoption-review-and-approval) — likely merge artifact

- EPIC-6: Duplicate S01 entries and orphaned S02-sms story — needs consolidation

- EPIC-8: Three variants of S01 (unit-testing-framework, unit-test-coverage, unit-and-integration-test-suite) — should be one canonical story

# 6. Code Quality Metrics

| Metric | Value | Assessment |
| --- | --- | --- |
| Type Safety (Pyright) | 0 errors, 0 warnings | COMPLETE |
| Linting (Ruff) | 0 errors | COMPLETE |
| Test Count | 204 passing, 0 failing | COMPLETE |
| Test/Code Ratio | 2.1x (tests are 2x production lines) | COMPLETE |
| Architecture | API / models / schemas / auth separation | COMPLETE |
| Critical Path Coverage | Animals, adopters, auth, donations | COMPLETE |
| E2E Tests | Not implemented | NOT STARTED |
| Performance Testing | Not implemented | NOT STARTED |

## 6.1 Test Distribution

| Test File | Count | Focus |
| --- | --- | --- |
| test_animal_schemas.py | 11 | Create/Update/Response validation |
| test_adopter_schemas.py | 15 | GDPR, email uniqueness, soft-delete |
| test_adoption_request_schemas.py | 12 | Request/status enums, transitions |
| test_config.py | 13 | Env override, defaults, validation |
| test_auth_utils.py | 14 | Password hash, JWT encode/decode |
| test_models.py | 30 | ORM instantiation, enums, relationships |
| test_animals.py (integration) | 16 | Full CRUD + auth enforcement |
| test_adopters.py (integration) | 19 | Soft-delete, 409 conflicts, GDPR |
| test_adoption_requests.py (integration) | 20 | Status machine, side effects, filters |
| test_auth.py (integration) | 11 | Login, RBAC, 401 enforcement |
| test_photos.py (integration) | 15 | Photo CRUD, ordering, cascade |
| test_donations.py (integration) | 26 | Donor/donation CRUD, Stripe, currency |

# 7. Recommended Next Steps

## 7.1 Immediate (Next Sprint)

- Clean up planning duplicates in EPIC-2, EPIC-6, and EPIC-8 to establish a trustworthy backlog

- Set up CI/CD pipeline with GitHub Actions (EPIC-9 S02) — enables safe iteration

- Implement Stripe webhook endpoint for donation completion (blocks revenue flow)

- Begin frontend technology decision (ADR-004) — Next.js recommended for SSR + SEO on catalog pages

## 7.2 Short-Term (Next 2-4 Weeks)

- Build admin dashboard (EPIC-7) — staff cannot operate the shelter without it

- Implement email notifications for adoption confirmations (EPIC-6 S01)

- Deploy to staging environment with SSL (EPIC-9 S03)

- Public animal catalog frontend — the highest-impact user-facing feature

## 7.3 Medium-Term (Phase 2-3)

- WhatsApp integration for adoption notifications (Paraguayan context: 97.5% penetration)

- Medical records module (EPIC-4) — required for Ley 4840/2013 compliance

- Local payment methods: Tigo Money, Personal Pay, PagoExpress

- Volunteer management with shift scheduling (EPIC-5)

End of Report

Generated March 26, 2026 — AI Whisperers